## Sheet1
Level | Main Screen | Parent Screen | Dev | Design | Notes
Root | Walkthrough | - | Complete
Root | Register Email |  | Complete
Root | Register Phone |  | Pending
Root | Register Social |  | Pending
Root | Login - Email |  | Complete
Root | Login - Phone |  | Pending
Root | Login - Social |  | Pending
Main | Groups Listing |  | Complete
Main | Direct Chats |  | Complete
Main | Friends - Listing |  | Complete
Main | User Info |  | Complete
Groups | Groups Chat |  | Complete
Groups | Polls |  | Complete
Groups | Resources |  | Complete
Groups | Group Info |  | Complete
Polls | List Polls |  | Complete
Polls | Create a New Poll |  | Complete
Polls | View Poll |  | Complete
Resources | List Resources |  | Complete
Resources | View Resource - Contact |  | Pending
Resources | View Resource - Upload |  | InProgress
Resources | View Resource - Link - is this really required? |  | Pending
Resources | Create Resource - Contact |  | Complete
Resources | Create Resource - Upload |  | Pending
Resources | Create Resource - Link |  | Pending
Features | Group Chat - Tag a message a resource |  | Pending
Features | Rate Resources and Write a comment |  | Complete
Features | Comment when voting in a poll |  | Complete
Features | Pin a resource |  | Complete
Features | Filter on resource page |  | Pending
Features | Broadcast? |  | Pending
Features | Events |  | InProgress
Features | Group Chat - Improve System updates vs users chat (keep them separate) |  | Pending
Features | Joined Group List screen separate to current group screen |  | Pending
Features | Registration ask for Country |  | Pending
Features | Groups to be country specific |  | Pending